## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Capture Marksheet | Yes | Yes | High | Complete | 18 | Yes
Design and develop app interface | Yes | Yes | Medium | Complete | 6 | Yes
Implement functionality to open camera interface | Yes | Yes | Medium | Complete | 6 | Yes
Testing opening camera interface and capturing images | Yes | Yes | Medium | Complete | 6 | Yes
Image Review | Yes | Yes | Medium | Complete | 5 | Yes
Develop a image review feature | Yes | Yes | Low | Complete | 2 | Yes
Confirmed Image is visible to user | Yes | Yes | Low | Complete | 3 | Yes
Image send to ocr engine to extract the data | Yes | Yes | High | In Progress | 0 | No
OCR Integration for question paper | Yes | Yes | Medium | Complete | 18 | Yes
Set up OCR library or API within the application for question paper. | Yes | yes | Low | Complete | 6 | Yes
Test OCR integration with sample question paper sheets. | Yes | yes | Medium | complete | 6 | Yes
Develop functionality to recognize and extract text data from Question paper sheets | Yes | Yes | High | complete | 6 | Yes
user creation and authentication | Yes | No | Medium | Not Started | 25 | No
Develop user authentication system for university administrators | Yes | No | Medium | Not Started | 10 | No
Implement admin functionality to create and monitor users. | Yes | No | Medium | Not Started | 10 | No
Test user authentication and admin functions | Yes | No | Medium | Not Started | 5 | No
Ocr integration for answer sheet | Yes | No | Medium | In Progress | 48 | Yes
Set up OCR library or API within the application for mark sheets. | Yes | No | Low | In Progress | 2 | Yes
Test OCR integration with sample mark sheets. | Yes | No | Medium | In Progress | 45 | Yes
Develop functionality to recognize and extract text data from mark sheets | Yes | No | High | In Progress | 1 | Yes
Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started