## Sheet1
Agile Test Plan
Project Name | OCR MARKSHEET |  | Browser: | Chrome
Test Case ID | 1 |  | Version: | Version 120.0.6099.225 (Official Build) (64-bit)
Written By: |  |  | Description:
Tested By: | Vamshi Bachu and Bharat Simha Reddy |  | Tested On: | 2024-03-15
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2024-03-15 | User selects the camera option to capture | Camera interface opens | Asked permission and camera | pass
interface opened successfully
2 | 2024-03-15 | User aligns the marksheet properly and | Image is captured | Captured successfully | Pass
captures image
3 | 2024-03-15 | User reviews the captured image before | able to confirm the image | Asked for confirmation or option to retake | Pass
confirming
4 | 2024-03-22 | OCR processes the captured Question Paper image | Question number and Co's information are extracted | Question number and Co's and respected levels are extracted | Pass
5 | 2024-03-29 | Ocr engine converts extracted Question paper data into structured table | Question paper Data is organized into a structured table format | Question Paper Data is organized into a structured table format | Pass
6 | 2024-04-10 | OCR processes the captured Answer Sheet image | Marks and student information are extracted | Marks and student information are extracted | No
7 | 2024-04-10 | Ocr engine converts extracted Answer sheet data into structured table | Data is organized into a structured table format | Data is organized into a structured table format | No
8 | 2024-04-15 | Admin adds a new user | New user is successfully added | New user is successfully added | No
9 | 2024-04-15 | User logs out of the OCR MARKSHEET application | User is successfully logged out | User is successfully logged out | No
10 | 2024-04-15 | Admin deletes | User successfully deleted | User successfully deleted | No
Create a Test Plan in Smartsheet

## Sheet2
0
1
0
1
0
0
0
0
0
0
0
0
0
0
0